## CRA
Ref No. | Risk Item | Baseline Position | Summary Position of Document | Cl. ref | Proposed Qualification / Treatment / Mitigation | Approval Required (Y/N) | Approval Level | Summary Position of Document / Submission [Complete then delete guidance notes] | Event | EOT | Delay Costs | Variation / other costs | Notes
1.1 | Conditions for access to documents | If agreements or confidentiality undertakings are required to be provided or declarations to be made before access to Invitation to Tender documents will be provided, those documents must be reviewed to determine what if any significant risks are included within them. |  |  |  |  | HOL
1.2 | Tender stages and validity period | If the tender submission is structured in stages, understand what this means to development of what constitutes a tender that is capable of acceptance (i.e. early contractor phase, is there a BAFO?)Is there a shortlisting? Is there a preferred stage with conditions to award or closure?Is the tender validity period unacceptably long? Does this raise issues of pricing for escalation? Be aware of impact of significant extension in validity period and qualify or price accordingly. | [Summarise validity and procurement process] |  |  |  | PCL
1.3 | Probity, process & confidentiality | Do probity and process obligations apply over and above the usual confidentiality obligations. If yes:implement a Probity and Process Plan submit all required signed deeds and declarations.Do anti-collusion and anti- corruption requirements specifically apply? If yes submit all required declarations. |  |  |  |  | HOL
1.4 | Tenderer releases & warranties | Any releases of liability in favour of the client must relate only to tender information and processes and must not extend to the contract or conduct during the contract phase.Any warranties given to the client must relate only to tender |  |  |  |  | HOL
1.5 | Tender conformance | If a conforming tender is mandatory (even as an alternative), can DTI comply? | [Outline any concerns regarding ability to conform] |  |  |  | HOC
1.6 | Security for bidding (‘bid bonds’) | Bid bonds must be limited to government clients and must be of a value no greater than 3% of the estimated contract value unless CEO approval has been obtained.The conditions of tender must provide for the terms of the calling of the bid bond and the basis of entitlement must be limited to a material breach (usually failure to submit a conforming tender with required validity period).The conditions of tender must provide for bid bonds to be returned no later than 14 days after:notice the tender has been unsuccessful;notice the tender has been successful;financial close for the project; orthe tender validity period has expired.Bid bond duration should not exceed the validity period or, ideally, 6 months from lodgement of tender.Where possible, an expiry date should be included in the bid bond.“No injunct” clauses should not be agreed to in respect to recourse to a bid bond.There must be no replacement or top up provisions in relation to bid bonds. | [Summarise bid security regime] |  |  |  | HOF
1.7 | Tender cost recovery | If tender costs are recoverable from the client, tender cost recording must be implemented to meet any actual or usual audit requirements. | [Summarise recovery regime] |  |  |  | HOF
1.1 | Client identity | It is our business’s baseline position is to contract directly with the client and not with:a subsidiary with limited assets; ora trust or trustee; or a special purpose vehicle (SPV). |  |  |  |  | Mgmt CMT | [Contracting entity][Corporate structure][Is our business contracting with a trust or other Special Purpose Vehicle][ASIC searches should be conducted where required]
1.2 | Client credit risk | A Credit Check is mandatory for all non-government clients. If the credit risk assessment is unsatisfactory then security of payment greater than our business’s exposure is required.This may include:a client provided parent company guarantee from an entity based in Australia with suitable financial capacity; &/ora client provided security, bond or unconditional undertakings; &/oragreed upfront prepayments from the client; &/ora tripartite agreement with approved financiers. |  |  |  |  | HOF | [Proper due diligence is required][Financial capacity of client][Client’s position as an Authority] [A credit risk assessment of all non-government clients must be carried out][Audited balance sheet statements and financial reports must be available][PPSR Registrations should be checked]
1.3 | Foreign exchange risk | Where Foreign exchange risk is taken, adequate measures must be implemented to mitigate risk. Our Business’s Head of Finance must approve and implement these measures. |  |  |  |  | HOF | [Amount / currency / exchange rate / hedging cover][List goods being procured from overseas][Contracts which include a requirement for forex risk (either upstream or downstream) should include hedging covers in the tender price][Preference is to negotiate terms where the client does not pay in foreign currency or have the exchange rate locked in at contract award][Pass through any foreign exchange risk to suppliers or subcontractor using fixed exchange rate]
1.4 | Rise and Fall (Escalation) | Our Business will constantly monitor market conditions to provide guidance regarding management and mitigation measures for Rise and Fall (Escalation) risk.our business’s baseline position is that the estimate must include:A review of current market conditions, including feedback from current projects, suppliers and subcontractors, and published data such as Australian Bureau of Statistics Producer Price Indexes,An estimate of price escalation based on the forecast project cashflow. Separate escalation factors should be applied for each of the key price components including at a minimum, Staff, Labour, Steel, Fuel, Concrete, Precast Concrete, Quarry Materials, Purchased Plant, Hired Plant, and Consultants Costs. A risk provision for Escalation over the estimate escalation allowance. This should be based on a sensitivity analysis of the escalation factors.For all tenders, consideration must be given to whether the contract should provide a regime of relief for rise and fall for key indices. If the contract does include partial relief for escalation, then consideration should given to whether or not this relief should be extended to cover more elements of the price. The bid position for Escalation must be approved by our business Management. | [5 empty] | [Review of current market conditions][Price estimate for Escalation][R&O provision for Escalation over Estimate allowance]
1.4 | Project or third party financing | Our Business must not provide project funding &/or investment equity without express approval from the Board.Where project funding &/or investment equity or third party financing is proposed:A proper investment decision supported by a business case must be completed;our business must not accept liabilities to third party funders which increase the aggregate liability, or are different to the liabilities, accepted under the underlying contract; andA full and separate review of all commercial, financial and legal liabilities and documents must be undertaken by the Head of C&C (or nominee) and legal counsel. |  |  |  |  | HF | [Financing party / liabilities to financiers / step in rights / fetter on exercise of rights][Does the contract require our business to provide any equity or debt financing in support of the project][Does the contract or side agreement assign obligations between our business, the asset owner, and the project financier(s)][Ensure requirements and obligations are consistent and appropriate for GA e.g. cure periods, notification periods, dealing with insurance proceeds, evidence of funding for variations][Ensure satisfaction of a liability to one party (e.g. the Principal) will be deemed to satisfy the liability to the other party (e.g. the financiers) – i.e. no dual / layered liability]
1.5 | Assignment / novation | The baseline position is the client must not be entitled to assign or novate rights and obligations under the contract to any third party without our business’s consent.Any consent by our business to do so should not to be unreasonable withheld.Where there is a government client, our business may accept novation to another entity within the client’s “cluster”. |  |  |  |  | HF | [Outline rights][Fettered / unfettered][Consent][GA must retain power of veto subject to the client demonstrating that any assignee or new entity has the financial and performance capacity to meet its contractual obligations][Due diligence required with a credit risk assessment][Track record and reputation of client should be assessed including any client-related parties and subsidiaries to which the contract could conceivably be novated or transferred to]
1.6 | Provision of confidential financial records | Where the contract provides the client the right to audit our business’s (and/or its downstream contractor’s) confidential financial records, including copies of audited accounts - prior consent must be obtained from our business’s Head of Finance. |  |  |  |  | HF | [Does the contract include a client right to audit and examine our business and/or our downstream contractor’s confidential financial records, including copies of audited accounts][This limit may not apply to alliance agreements and other similar cost reimbursable contract models where client rights to audit underpin the model]
2.1 | Payment Terms | The baseline position is where the contract does not provide an express right of suspension of works for non-payment, our business should be entitled to rely on its right to suspend under Security of Payments legislative regime.Payment terms should be generally accepted within the industry. |  |  |  |  | HF | [Outline Cycle / timing][Basis of payment: SoR / lump sum / BoQ][Terms: Period from performance to payment][SOPA / BCIPA Reference Date][Is there an impractical list of obligations that are precedents for payment][Are there disproportionate remedies for relatively immaterial compliances against this list][Does the contract provide for payment within the companies standard payment terms (30 days from end of month of invoicing)] [Timing needs to include dates for submitting claims and client to approve claim then payment to be made][Payment must be made for full value of work completed in the claim period] [Payment terms / cycle not later than 2 months after work is performed][Any conditions precedent to payment must be able to be readily met and within GA’s control][GA preferred position is that client’s failure to make payment in accordance with the contract is an express Client Event of Default (breach of contract)]
2.2 | Cash flow | Prior to submitting a tender:A cash flow must be prepared that includes forecast expenditure and revenue. The cashflow must show at a minimum, a neutral cash position during all phases of the project (with a reasonable “buffer” built into account for the inherent uncertainty over cashflow forecasts). Where the cash flow demonstrates a negative cash position, departures or qualifications should be included in our business’s offer to ensure the minimum of a cash neutral position.Any departure from a cash neutral or positive position must be approved by our business management. |  |  |  |  | HF | [Confirmation that the cash flow has been prepared prior to submission][Does the cash flow forecast a positive cash position for the project duration][Is the cash positive position reliant on the client’s acceptance of proposed departures or qualifications][Project should remain cash positive for the duration][Consideration should be given to Day 1 payments to ensure cash positive position][Bid team to prepare a detailed cash flow (positive or negative)][Any interest and financing costs resulting from a negative cash flow must be included in the tender price]
2.3 | Set-off | Our Business baseline position is to only accept set off clauses which are subject to:Set off only be allowed in respect of bone fides claims of the client under the contract; andthe Contract not including clauses that give the client the right to set-off outside the contract or between multiple work packages within the one project or program of works.A departure from this must be approved by our business management. |  |  |  |  | HCC | [Outline rights / trigger][Does the client have the right to set-off payment outside of the contract or between multiple work packages within the one project or program of works] [If client operates out of Region, CD briefing and approval required]
2.4 | Rights for non-payment | Our Business‘s baseline position is the client’s failure to make payment in accordance with the contract is an express Client event of default (i.e. a breach of Contract). |  |  |  |  | HCC | [Suspension rights / SoPA rights amended][Interest accrued on late payment][Termination trigger for prolonged delay][Does the contract contain any non-standard conditions in regards to claims made under the relevant Security of Payments legislation][Seek entitlement to suspend work for late payment] [Interest to accrue at bank bill rate][Include contract conditions describing the client’s failure to make payment in accordance with the contract as an explicit Client Event of Default][Where the Contract does not provide an express right of suspension for non-payment, GA should be entitled to rely on its right to suspend work under the SOPA / BICPA if the client is a state government entity]
2.5 | GST | The contract should state whether pricing is exclusive or inclusive of GST. If not clear, then a clarification must be included in the tender submission. |  |  |  |  | HF | [Check whether the contract specifies that payments are to be exclusive of GST]
2.6 | Certification | Our Business must not accept payment conditions:that include contract payment clauses containing an impractical list of obligations that are precedents for payment; orwhere associated disproportionate remedies for relatively immaterial non-compliance against this list. |  |  |  |  | CM | [Who assesses Principal, superintendent or independent][Outline process, timing][Determinations to payment must be objective and measurable against defined criteria][Clear method of measurement][Retain ability to dispute assessment] [Who is certifying the payment? Are they credible and objective? Are they independent?]
2.7 | Payment for offsite / unfixed plant, equipment, materials | The baseline position is our business is entitled to payment for offsite materials. |  |  |  |  | CM | [Entitlement / limitations / unfixed materials / letter of lien / transfer of title / security required][Secure entitlement to claim for off-site / unfixed materials] [List all long lead time procurement items (materials / plant / equipment) that will require upfront payment and impact cash flow][The estimate should make allowance for the cost of any securities required to secure the payment.]
2.8 | Bonds and PCGs | The level of bonding for a project must be approved by the our business Head of Finance.Where a PCG (or bonding) is required, the form of guarantee must be approved by the Board. The PCG Request form must be used to obtain Board approval and included within the Board papers. The our business Head of Finance must obtain Board approval. |  |  |  |  | Board | [Entity to provide / standard (approved) form / differences from standard / scope / limit on liability][PCG not to expose the parent entity to risks extending beyond ensuring performance of subsidiary obligations][PCG must be subject to the overall cap on liability][The PCG must not contain any greater obligations than those assigned to GA under the head contract][Even with Board approval to provide a guarantee, under no circumstances shall the PCG contain any greater obligations than those assigned to our business under the head contract]
2.9 | Performance security | Where our business is required to provide a performance security, then:The contract must expressly state that the purpose of the unconditional undertaking(s) is to provide security for performance under the contract.It is our business’s preferred position that client must not be entitled to convert the unconditional undertaking(s) to cash for any reason other than in respect of amounts due and owing or default.Where the total security is greater than 7.5% of the contract value, our business Management approval must be sought. |  |  |  |  | HGP | [Is our business required to provide security][Does the contract provide for a reinstatement provision on security that has been called by the client][Does the contract provide for a validity of security that extends beyond the Adjusted Contract Duration (practical completion plus approved extensions of time) including the Defect Liability Period][Minimum rating][Expiry Date (yes/no)][Entity providing / stated purpose / amount & form / conditions for access to, reduction and return / top up requirements][Not greater than 7.5% of Contract Value][50% reduction at Completion] [Return within 30 days of DLP expiry] [No greater rating than the issue’s current rating][Right to convert to cash limited to amounts due and owing] [Top up only once for a maximum of 10% of the original contract sum] [There must be no obligation to replace (or top up) an unconditional undertaking that has been cashed][Replacement only where the credit rating of the issuer falls below current rating]
3.1 | Access and Possession | Our Business must be:given Access and Possession to all areas where the physical works are to be undertaken;able to obtain a copy of any agreement between a third party and the client that relates to Access and Possession.Access and Possession must be certain and such as required to enable our business to perform its obligations under the contract (including to adjacent properties where required). Where Access is not provided our business must be entitled to cost and time relief. |  |  |  |  | CD | [Does the contract provide for cost and time relief (including the cost of delay) for acts or omissions of 3rd parties not contracted to and under the control of our business, where such parties may prevent or limit our business’s access to the Site][Limitations][Land acquisition required][Define process for obtaining access to carry out works on road & motorways e.g. road occupancy licence, lane closure regime][List Authorities that have right to grant or limit access][Must be a defined regime for handover of access to Contractor complete with schedule and dates][Failure to provide must constitute breach or give rise to adequate time and cost relief] [Access must be sufficient to perform all the works required under the specification / scope] [Bid team to undertake proper due diligence of information contained within all contract and information documents (e.g. technical and engineering reports)] [GA should qualify or price the risk of any extra land it needs to obtain to construct the Works under the contract (including land to be used as compound or laydown areas)]
3.2 | Site Conditions / Site Risks | The baseline position is our business should be entitled to time and cost relief associated with:material changes from information provided by the client or in assumptions stated in the tender; orfor latent conditions / site conditions that could not reasonably have been anticipated by our business at the time of tender.Where the Contract requires our business to take the risk on latent conditions / site conditions, our business must not do so unless the risk(s) are fully understood, priced, programmed, qualified, mitigated or limited. Our Business tender team must:review the range of geotechnical, building condition / structural, utility, engineering and environmental documents provided by the client;consider opportunities to undertake a broad range of additional geotechnical, asset condition, environmental or other relevant investigations after being selected as preferred contractor (either prior to award or promptly following award);include an amount in its price in relation to this issue;discuss / agree commercial models with the client to account for this risk which often include, Target Costs, re-measurable scope / quantities, key assets / utilities / contaminated areas which may be carved out of lump sum pricing, sub-liability caps which limit our business’s capped exposure in certain areas of the scope.Should the tender team recommend our business withdraw departures and accept such risks, detailed investigation and briefing papers must be presented for approval to our business management.Detailed consideration within Risk and Opportunity allowance must also be set out by the Estimation team. |  |  |  |  | CD | [Does the contract explicitly provide for cost and time relief (including the cost of delay) for latent conditions / site conditions that could not reasonably have been anticipated by our business at the time of tender][Client or Contractor risk][Scope of entitlements][Definition of Site Conditions needs to be expressly stated and sufficient][The bid team should attend any site investigation meeting and allow in the tender price the risks, contingencies and circumstances which might affect the works][Bid team to undertake proper due diligence of information contained within all contract and information documents (e.g. technical and engineering reports)] [Where the contract does not provide for cost and time relief for latent conditions / site risks explicitly identified and described in the tender documents, the bid team should do thorough site investigation and allow in the tender price the risks, contingencies and direct costs which might affect the works e.g. rock, unsuitable, acid sulphate soils, asbestos, utilities, ground water]
3.3 | Existing &/or Unknown Services | The baseline position is that our business should be entitled to time and cost relief associated with:any unforeseeable change in the condition or location of existing services; the impact of unknown services that could not reasonably have been anticipated by our business at the time of tender;additional 3rd party requirements for betterment, improving or enhancing utility assets;Where the contract requires our business to take the risk on existing or unknown services, our business must not do so unless the risk(s) are fully understood, priced, programmed, qualified, mitigated or limited.There must also be a distinction and analysis made by the tender team between contestable and non-contestable utility works. Our Business baseline position is to not take the cost or program risk on non-contestable utility works.The tender team must:review the range of services plans and documentation provided by the client;undertake a broad range of additional services investigations after being selected as preferred contractor (either prior to award or promptly following award);include an amount in its price in relation to this issue;identify key assets which are determined to be of risk to our business, and develop a detailed management plan to address those risks (for each asset). Should further information be required from the client to address and manage those risks, that information must be requested ASAP during the tender.Should the tender team recommend our business accept such risks, detailed investigation and briefing papers must be presented for approval by our business Management. Detailed consideration within Risk and Opportunity allowance must also be set out by the Estimation team. |  |  |  |  | CD | [Does the contract explicitly provide for cost and time relief (including the cost of delay) for existing &/or unknown services][Client or Contractor risk][Scope of entitlements][List all PUP required to protect, relocate and modify to perform the scope of work][Definition of existing &/or unknown service needs to be expressly stated and sufficient][The bid team should attend any site investigation meeting and allow in the tender price the risks, contingencies and circumstances which might affect the works][Bid team to undertake proper due diligence of information contained within all contract and information documents (e.g. technical and engineering reports). [Where the contract does not provide for cost and time relief for Existing &/or Unknown Services explicitly identified and described in the tender documents, the bid team should do thorough site investigation and allow in the tender price the risks, contingencies and direct costs which might affect the works]
3.4 | Existing Structures (incl. Engineered Embankments and Pavements) | The baseline position is our business should be entitled to time and cost relief associated with:an unforeseen change in the condition of existing structures (eg, foundations, buildings, engineered embankments and pavements etc); orthe impact of existing structures that could not reasonably have been anticipated by our business at the time of tender.Where the contract requires our business to take the risk on existing structures (incl. engineered embankments and pavements), our business must not do so unless the risk(s) are fully understood, priced, programmed, qualified, mitigated or limited.The tender team must:review the range of condition reports, structural plans and documentation provided by the client;undertake a broad range of additional engineering investigations;include an amount in its price and Risk and Opportunity in relation to this issue;identify key structures which are determined to be of risk to our business, and develop a detailed management plan to address those risks (for each asset);The detailed management plan must be priced and programmed;Should further information be required from the client to address and manage those risks, that information must be requested ASAP during the tender.Should the tender team recommend our business accept such risks, detailed investigation and briefing papers must be presented for approval by our business Management. |  |  |  |  | CD | [Does the contract explicitly provide for cost and time relief (including the cost of delay) for the condition of Existing Structures (incl. Engineered Embankments and pavements)][Client or Contractor risk][Does the client provide any warranties in relation to the ground preparation / working platform if GA has not prepared this][Scope of entitlements. List all Existing Structures required to protect, relocate, modify to perform the scope of work][Definition of existing structures (incl. engineered embankments and pavements) needs to be expressly stated and sufficient][The bid team should attend any site investigation meeting and allow in the tender price the risks, contingencies and circumstances which might affect the works][Bid team to undertake proper due diligence of information contained within all contract and information documents (e.g. technical and engineering reports)] [Where the contract: does not provide for cost and time relief for Existing Structures (incl. Engineered Embankments and pavements) explicitly identified and described in the tender documents; the bid team should do thorough site investigation and allow in the tender price the risks, contingencies and direct costs which might affect the works]
3.5 | Native title claims and artefacts liability | The baseline position is our business should be entitled to time and cost relief associated with discovery of an historical artefact or native title claims.our business should only accept responsibility for risk associated with the existing heritage or artifact conditions including:historical artefacts;native title claims;to the extent the risks are able to be fully understood, priced, qualified, mitigated or limited.Wherever possible, the tender team should seek to negotiate a cost plus, re-measurable or Target Cost commercial model for heritage and artifacts works, however, only where the scope is able to be priced and programmed. |  |  |  |  | CD | [Does the contract provide for cost and time relief (including the cost of delay) for the discovery and treatment of artefacts other than those explicitly identified and described in the tender documents][Does the contract include a foreseeability test that is not limited to specific artefacts, their location, and treatment as described in a CHMP or similar] [Does the contract provide for cost and time relief (including the cost of delay) for both new and existing claims to Native Title over any part of the Site][Client / Contractor risk][Scope of entitlements][Bid team to undertake proper due diligence of information contained within all contract and information documents (e.g. technical and engineering reports)][Where the contract: does not provide for cost and time relief for the discovery and treatment of artefacts other than those explicitly identified and described in the tender documents; includes a foreseeability test and that test is not limited to specific artefacts, their location, and treatment as described in a CHMP or similar.the bid team should do thorough Site investigation and allow in the tender price the risks, contingencies and direct costs which might affect the works]
3.6 | Contamination | The baseline position is our business should be entitled to time and cost relief associated with the discovery of contamination not caused or disturbed by performance of our business’s works.Only under exceptional circumstances will our business accept the risk of contamination on, under or in the vicinity of the site. Our Business must not accept liability for:unknown pre-existing contamination;trace to source obligations; orclaims by third parties connected with contamination which do not relate to work undertaken by our business.Wherever possible, the tender team should seek to negotiate a cost plus, re-measurable or Target Cost commercial model for contamination works, however, only where the scope is able to be priced and programmed.Should the tender team recommend our business accept any contamination risk, detailed investigation and briefing papers must be presented for approval by our business Management. |  |  |  |  | GMD | [Does the contract provide for cost and time relief (including the cost of delay) for ‘trace to source’ contamination risk that cannot be properly and fully quantified, and therefore is not included in our business’s price and program, at the time of tender][Does the contract provide for cost and time relief (including the cost of delay) for any other contamination risk that cannot be properly and fully quantified, and therefore is not included in our business’s price and program, at the time of tender][Client or Contractor risk][Scope of entitlement][Definition of Contamination][GA must not take the risk to chase contamination back to source][Qualify so that GA only takes the risk of contamination identified, physically encountered and disturbed by the carrying out the works][Document all known conditions at site / Reports provided and ability to rely][Consider effect on groundwater and disturbance of contaminated groundwater associated with any excavation works][The bid team should undertake a thorough Site investigation and allow in the tender price the risks, contingencies and direct costs which might affect the works]
3.8 | Client supplied information | The baseline position is our business should be entitled to rely on client supplied information.Where the contract requires our business to accept the risk on client supplied information, our business may:warrant that is has not relied on client supplied information; andwaive rights to any claims by our business in respect of such information,to the extent it is able to, and has:carried out adequate due diligence relating to the underlying risks with which the information is concerned; andthe tender team has been confirmed that no reliance on Client supplied information is required for the contract.Where due diligence is not possible during the tender process, i.e. site access is not available, the client is the only party able to obtain requisite information, probity restricts our business’s due diligence etc, the tender team must identify key client supplied documents and information which has been used to price and program the tender submission, and negotiate reliance on that information. Whilst client’s are unlikely to provide relief for broad categories of documents, i.e. “all geotechnical data and reports”, if our business can identify key documents, why reliance is required and what assumptions our business made within its tender due to those documents etc the client may be more inclined to agree a reliance regime within the contract. |  |  |  |  | CD | [Client or Contractor risk][No reliance warranties as to completeness, accuracy, suitability][Tender period and contract period][Bid team to undertake proper due diligence of information contained within all contract and information documents (e.g. technical and engineering reports)] [Bid back all documents the estimate and program has relied upon in developing the tender][Create a category of “Reliance Information” for which relief is available should conditions/circumstances materialise that a reasonable contractor could not have reasonably anticipated]
3.9 | Planning approval | Our Business must not accept risk or responsibility to obtain Planning / Development Approval, or to comply with unknown conditions of a Planning / Development Approval.Where our business is asked to do so, the Head of C&C must be consulted and external legal advice sought from external planning specialists where required.Should the tender team recommend our business accept any planning approval risks, briefing papers must be presented by the tender team for approval by our business Management. |  |  |  |  | CD | [Does the contract expose our business to an unknown list of conditions of approval associated with building/heritage/noise criteria for the completed works, issuance of titles, or liabilities/obligations passed through by statutory authorities, the effects of which cannot be readily quantified in terms of cost and time impacts at the time of tender][Client or Contractor risk to obtain][Approval status & timing][List conditions of approval][Legal challenges][All approval conditions must be known at time of tender, if not qualify to preserve an entitlement to claim time/cost (if any) once published][Demonstrate the estimate and program include adequate allowance and contingency for compliance with each condition of approval][Bid team to do due diligence on the approvals and consents required in relation to the contract and the work under the contract and identify those to be allocated to the principal and the contractor]
3.10 | Other consents, permits, licences and approvals | Our Business should only accept risks or responsibility to obtain approvals, consents, licences, permits that are part of ‘business as usual’ construction requirements.our business must not accept responsibility to comply with unknown conditions of consents and approvalsGamuda Australia must not accept delay risk associated with the granting of other consents/permits/licences/approvals beyond any delay contingency made where the obtaining of permits, licences and approvals is outside of the control of our business. |  |  |  |  | CD | [Client or Contractor risk to obtain][Does the contract expose GA to an unknown list of conditions of approval associated with building/heritage/noise criteria for the completed works, issuance of titles, or liabilities/obligations passed through by statutory authorities, the effects of which cannot be readily quantified in terms of cost and time impacts at the time of tender][List relevant permits, consents, licences required to perform the works and approving Authorities / 3rd parties e.g. road occupancy limitations / Legislative restrictions on night shifts] [Approval conditions][Demonstrate the estimate and program includes adequate allowance and contingency for obtaining and/or compliance with each approval][List all the approvals that GA is required to obtain for the project. Is this BAU, if not, price or bid back]
4.1 | Early Works | Our Business must not agree to perform any Early Works unless a binding agreement is in place. |  |  |  |  | CD | [Are there any?][Documentation for Early Works][Separate form of agreement ECI][Payment regime][Outline scope of the Early Works][A briefing of Early Works and Head Contract Agreement should be provided to the Head of C&C (or nominee)]
4.2 | Interface Risk (Other Contractors) | Our Business should be entitled to time and cost relief associated with any third party construction interface over which it has no control.All Interface Agreements must be briefed to the Head of C&C.Where the bid team recommend departure from this base position approval must be sought from our business Management. |  |  |  |  | CD | [Document all third party construction interfaces / access limitations][Separate interface agreement required][Client or Contractor risk?][Obligations to co-operate, coordinate and plan.][Risk of liability for other contractor delay.][List all third party works interfaces.][Full review required of any separate interface agreement or access protocol] [Demonstrate the estimate and program include adequate allowance and contingency for all known interfaces][Particular note should be taken of the reliance on Authorities or Asset Owners to complete works,or provide resources to meet our program. Where this is the case, sufficient float must be included in the program.][Third party interface must remain the risk of the principal.][Delay or disruption caused by other contractors must give risk to adequate time and cost relief.] [Consideration or WHS Principal Contractor duties are applicable.]
4.3 | Head Contract Pass-Throughs / Supply Chain Sub-Contractors / Suppliers / Consultants | Where suppliers or subcontractors are to be novated to our business:their subcontract documentation and prior work is to be assessed during the tender for compliance within our business’s Key Contract Risks and Conditions, and any gap risk with the Head Contract must be assessed in detail; andthe novated agreement is to be reviewed by the Head of C&C and/or legal counsel to ensure consistency with the our business’s contract with the client.our business must have the right to reject suppliers, subcontractors or consultants nominated after the date of contract, unless the client retains responsibility for their acts or omissions.All Novation Deeds must be referred to Head of C&C (or nominee).Preferably, our business should not accept contract conditions where the contract includes a positive obligation to pass through head contract obligations to downstream contracts without any limitation to ‘best endeavours/what is commercially available’, and without limitation to the smallest possible group of downstream contracts. Should the client require this, the head contract obligations ought to be minimized and market tested. That market testing feedback should be provided to the client in the tender process, for example, key suppliers should be contacted during the tender phase and provided with a copy of the head contract pass-down provisions. Departures from those provisions should be provided to the client and a narrowed position negotiated wherever possible. |  |  |  |  | HCC | [Does the contract contain a positive obligation to pass through head contract obligations to downstream contracts without any limitation to ‘best endeavours/what is commercially available’, and/or without limitation to the small possible group of downstream contracts][Geographical limitations on use of consultants / suppliers / subcontractors][Nominated / novated consultants / suppliers / subcontractors][Does the contract contain an obligation on GA to comply with the terms and conditions of the Head Contract][Client should not have the power to reject strategic procurement plan and engagement of subcontractors] [Any novation must be carefully assessed to understand performance and liabilities adopted][All subcontractors must be engaged under the GA standard suite of agreements] [Bid team to qualify any pre-agree critical / key subcontractors, suppliers &/or consultants in the tender][Bid team to test the supply chain market with proposed pass through conditions]
4.4 | Warranties for materials and equipment | The baseline position is our business should not accept contract conditions where:its warranty obligations to the client are in excess of that commercially and readily available from suppliers (i.e. warranting 100 year design life where suppliers only provide 20 year design life); orthe additional cost and time consequences cannot be accounted for within the tender submission for non-market warranties.Client deed polls requiring subcontractors, supplier and consultant warranties be provided directly in favour of the Client are becoming normal practice for client contracts. Such deed polls must be market tested during the tender process, with appropriate feedback provided to the client. |  |  |  |  | HCC | [Are our business’s warranty obligations to the client in excess of that commercially and readily available from our vendors][Have the additional cost and time consequences associated with such warranties (with limited downstream remedies) been documented and considered in the price and program][Is GA required to provide any warranties to the client in regards to GA provided materials (i.e. aggregates for own quarries, asphalt etc)][Ensure that all warranty obligations are documented and that management are briefed of the same at the tender review]
4.5 | Process Risk, Performance / Capacity Risk | The baseline position is our business should not accept contract conditions where the contract allocates any form of process risk, productivity or performance / capacity risk of others to our business. |  |  |  |  | CD | [Process risk refers to construction of a plant that is designed to alter the physical properties of a material or product][Performance/capacity risk refers to the movement or delivery of a material from one point to another or the quantum of a product produced by a constructed plant] [Does the contract allocate any form of process risk or performance/capacity risk to our business]
4.6 | Industrial relations | For each Project, our business must identify Industrial Instrument or Enterprise Bargaining Agreement (EBA) in place, and form a sound basis or the calculation of the associated labour rates and productivities that underpin the pricing.The tender team must consult with our business’s Industrial Relations Manager to confirm contractual requirements are capable of compliance. |  |  |  |  | HHR | [Is there a binding Industrial Instrument or Agreement in place (to form a sound basis or the calculation of the associated labour rates and productivities that underpin the pricing of our offer)]
5.1 | Delay Damages and Liquidated Damages | Our Business may accept the provision of Liquidated Damages (LDs) within a contract subject to:The limit of liability for LDs is capped at not more than 10% of contract value, or the LD burn rate is low enough to ensure that total LD liability is effectively capped at 10%,LDs must be the client’s sole remedy for delay.LDs must be included in overall liability cap. |  |  |  |  | GMD | [Bid team to specify burn rate calculation][Burn Rate: Margin or LD cap must not be exceeded within 20% of project duration][Bid team to ensure there is adequate program contingency to ensure LDs are not applied][If GA is in a subcontract arrangement - No pass through of head contract / client LDs or damages to be accepted] [Does the contract include clauses that give the client the right to deduct liquidated damages and other non-delay damages to more than 10% of the original Contract Sum in the aggregate, unless otherwise limited by a rate per period that is so low as to provide our business with adequate protection from LDs][Liquidated / at large / amount per period / cap / sole remedy][LDs cap accrue towards and sit within overall General Liability Cap]
5.2 | Entitlement to extension of time | The baseline position is our business should be entitled to extensions of time to any Contractual Completion Date (subject to notice provisions set out in the Contract) if there is a delay in achieving completion by a cause of delay beyond the control of our business, including any act, default or omission of the Client. Such delays are often called “neutral” causes of delay, where neither party is responsible for the delay. Extension of time entitlement is commonly provided by clients for “neutral” causes of delay.Where the Contract requires our business to accept the risk on a cause of delay which is beyond our business’s foreseeability or reasonably control, our business must not do so unless the risk(s) are fully understood, priced, programmed, qualified, mitigated, limited or allowed for. Our Business’s Head of C&C must be consulted prior to doing so |  |  |  |  | HGP | [Calculation of duration entitlement][EOT as Sole remedy][Client or Contractor owns the float][Does the contract include clauses that allocate ownership of float and/or Contractor’s Contingency to client parties] [Entitlement to be calculated by reference to the actual delay (and must be referenced to the then current program (not subject to client’s approval)][GA must retain the benefit of any float or contingency identified in the baseline program][Careful review of provisions regarding duty to mitigate and corrective actions must be undertaken to ensure EOT entitlement exists] [GA must ensure that any conditions precedent to EOT are achievable e.g. notice requirement and administration can be readily me.][Qualify so that the extension of time relief is not contingent on demonstrating critical path delay and achieving completion by the contractual date for completion]
5.4 | Entitlement to Delay Costs | In addition to EOT entitlement, our business should as a minimum be entitled to delay costs for client caused delays, including: acts or omissions of the client (including breach) or its agents, consultants and invitees;change in law, statutory requirements etc;client directed variations; andlegal challenge not relating to breach by our business (including native title applications).Where the contract requires the contractor to take the risk on the entitlement to an extension, our business must not do so unless the risk(s) are fully understood, priced, programmed, qualified, mitigated or limited. |  |  |  |  | CD | [Delay costs / compensation for additional costs][List quantum, formulae or basis of calculations][What costs are recoverable][Sole remedy for delay][GA should be entitled to recover its actual delay damages or ensure that any pre-agreed rate is sufficient to cover all delay damages that the business will incur (including for suppliers, subcontractors and consultants)][Estimating team to ensure that calculation for delay costs are transparent and retained. Approx. 30% uplift on actual calculations ;should be applied at tender]*
5.5 | Force Majeure (Insurable) and(Uninsurable) | Our Business must not enter Contracts without a force majeure regime.our business should be entitled to extension of time for Force Majeure Events (both Insurable and Uninsurable) except to the extent caused or contributed to by our business.The baseline position is our business should not accept:an obligation to reinstate damage caused by Uninsurable Force Majeure Events and these Events must be “Excepted Risks” under the contract; ora contract that does not contain an equitable list of Force Majeure Events with (at least) time relief against these events; ora contract containing clauses that limit the Force Majeure Events to only those occurring in Australia.The force majeure regime within the contract must contain equitable recovery in the event of prolonged suspension, i.e. recovery of at least quantum merit – a reasonable value for works performed. |  |  |  |  | CD | [Does the contract contain an equitable list of Force Majeure events with (at least) time relief against these events][Does the contract contain clauses that limit the Force Majeure events to only those occurring in Australia][Does the contract provide for termination of the contract in the event of a prolonged and continuous Force Majeure event (irrespective of whether the rights are reciprocal or not)][List events & rights arising][Estimate should ensure adequate contingency in risk pricing to account for Force Majeure events]
5.6 | Notices and Time bars | Our Business should not accept time bars which relate to when the event giving rise to the claim or entitlement occurs irrespective of reasonable knowledge of the event by our business. |  |  |  |  | HCC | [List all time bars to relief][Document notice requirements][EOT / variations / latent conditions / general][Are notice requirements and administration able to met]
5.7 | Concurrent Delay | Concurrent delay should only be enforceable on critical path activity delays.. |  |  |  |  | HCC | [EOT if concurrent delay]
6.1 | Variations | Our Business must be entitled to variation for changes to the scope of works to be performed (including temporary works).No obligation should arise to perform variation works unless directed in writing by the Client.Preferably, the Client must not be able to avoid liability for variations on the basis of clarifying errors, ambiguities or inconsistencies in the Contract |  |  |  |  | CD | [Definition of variation.[Items explicitly excluded from variations][Cost recovery / valuation][Method of measurement.[Pay items][% margin application (additions / deductions)][Obligation to continue to perform as per direction prior to agreement on quantum][Preferably GA should limit client’s ability to reduce scope of work and award to another contractor]
6.2 | Change in lawChange in codes standards and specifications | The baseline position is our business should be entitled to time and cost relief by way of variation for:compliance with changes in law affecting the works;compliance with changes in standards affecting the works;compliance with changes in specifications affecting the works. |  |  |  |  | CD | [Does the contract explicitly provide for cost and time relief (including the cost of delay) for a change in law after Contract Award, where such a change is likely to affect our business’s performance of its contract obligations[Client / Contractor][Project specific/ specified / general][The definition of Law should extend to codes, standards, specifications, policies, procedures and administrative processes][Note the revision / edition of all standard specifications in place at date of contract as a baseline for change]
6.3 | Provisional Sums | The baseline position is our business should not accept program risk on provisional sum items. Our Business should be entitled to time and cost relief where provisional sums are exceeded. If the client is unwilling to negotiate this item, a “limits of accuracy” should preferably be negotiated with the client, i.e. should the provisional sum quantity change by +/-20%, time and cost relief should be provided. |  |  |  |  | CD | [List provisional sum items][List scope growth opportunity][% margin application] [Demonstrate that provisional sum items are accounted for in the estimate and program]
7.1 | Program | The baseline position is our business should not accept contract conditions that allocate ownership of float and/or Contractor’s Contingency to the Client.The tender team must include within tender briefings information as to “who owns the float” for each contract. |  |  |  |  | CD | [Are we proposing to submit a program with float Contingency][Does the contract include clauses that allocate ownership of float and/or Contractor’s Contingency to client parties][Strict compliance / obligation to comply][Monthly updates][Who owns the float?] [Is the program a realistic assessment of time required to complete the work][GA must retain flexibility to amend the contract programme as required (sequencing / staging / methodology)][If GA is a subcontractor, then GA must be provided with an updated head contractor’s program and look ahead]
7.2 | Completion & Sunset Date | Our Business’s baseline position is that we should not accept a condition for completion where:the completion test(s) are not:within our business’s control;objective, measurable and reasonably capable of being achieved;subject to the subjective opinion of a non-independent certifier; andcompletion is not the trigger for return of security, expiry of care of the works obligation, and extinguishment of Liquidated Damages liability.our business should not accept a condition of “defect free” completion (with the exception of minor defects that do not effect operation). However, noting the standard GC21 Construction Contract often used by TfNSW includes such clause which is often accepted by the market and managed at a Project level.The baseline position is our business should not accept a condition where a contract:contains a clause that provides for a period from Contract Award to the Sunset Date of less than 24 months from completion date; anddoes not provide for adjustment of the Sunset Date for Extensions of Time. |  |  |  |  | HCC | [Does the contract contain a clause that provides for a period from Contract Award to the Sunset Date of less than twice the Original Contract Duration][If the contract contains a Sunset Date, does the contract provide for adjustment of this date for Extensions of Time][Definition][Completion test objective, within Contractor’s control][Defect free / minor defects][Sunset date]
7.3 | Acceleration | A client may order Acceleration:to the extent necessary to overcome delay for which the our business is responsible; orprovided our business is entitled to payment.The baseline position is our business should not accept the obligation to accelerate upon direction if there are provisions that make payment for acceleration dependent on achieving a nominated accelerated date for completion. |  |  |  |  | CD | [Costs / obligation to achieve nominated date / breach if failure to achieve][Objection right if not achievable]
7.4 | Defects and Defects Liability | The baseline position is our business should accept a defects liability period longer than 24 months from the date of completion, with no more than one 12 month refresher period for any work the subject of defect rectification and capped at a maximum of 36 months (sunset date), to avoid ‘evergreen’ liability.our business must also:have the first opportunity to rectify a defect before the client can have another contractor perform the works;not accept defect rectification as a carve out from the general liability cap; andnot accept responsibility to rectify defects that are not caused by its own (or its design consultants, subcontractors, or suppliers) breach or wrongful act or omission |  |  |  |  | CD | [Does the contract provide for a DLP of greater than 24 months][Does the contract provide for resetting of the DLP in the event that defects are identified (rolling end stops)][Defects liability period / refresher period (evergreen?) / accept and retain monies] [Longer defects periods must be priced into the Estimate]
8.1 | Design[Select: Client ProvidedNovated Concept Design] | The baseline position is our business should not warrant that the client’s brief or mandatory requirements are “fit for purpose” for the Project. This is a matter for the client. Our Business should also not warrant a client provided design is “fit for purpose”. Again, this is a matter for the client and its designers.If our business must warrant the above, a reasonable amount for design rectification and assessment must be allowed in the price, program and Risk and Opportunity by the Estimating team. |  |  |  |  | CD | [Status of design development][Who has design responsibility - Client / Contractor][Any design novation? / Terms of novation acceptable][Requirement to complete design provided by the Client][Independent verification / compliance with client’s brief][Responsibility for preliminary design / Principal’s Project Requirements] [Where GA is asked to warrant “fit for purpose” a client provided design, GA must have the design independently verified such that the design or the client’s design consultants are novated on acceptable commercial terms][GA may accept responsibility for prior/concept design work carried out by third parties, subject to:verification of the prior design by GA’ design consultant; andpass through of risk to the GA’ design consultant][GA may accept design responsibility for temporary or permanent works only to the extent that:it has competent in-house design capability; ordesign is carried out by professional third party consultants and the third party consultant is contractually liable to GA in respect of the design; andGA is covered by adequate professional indemnity insurance]
8.2 | Fit for Purpose | Our Business should not warrant the client’s scope document or specification is “fit for purpose”.Where a “fit for purpose” warranty is provided it must be limited to a purpose stated in the contract that is clear, objective, measurable and achievable and that is not in excess of that commercially and readily available from our business’s designers.The preferred approach is to ensure that the “purpose” is defined in the general conditions. If this is not able to be agreed with the client, then a clear statement of purpose in the design brief to give certainty around this warranty in the event of a dispute should be required.Wherever possible, our business should limit the wording of its warranty to that which is provided by its design consultants, i.e. a back to back fit for purpose definition to be applied to the delivery phase should be agree with the main design consultants during the tender phase. |  |  |  |  | CD | [Does the contract require our business to provide a design that is “Fit for Purpose’ on a design agreement that either has or will be novated to us][Does the contract contain a Fit for Purpose definition that is in excess of that commercially and readily available from our business’s designers][Purpose definition][Is the purpose objective, measurable, achievable and stated in the contract][At completion / at all relevant times for design or completed works] [Preferably, GA must not warrant the works remain “Fit for Purpose” after completion (e.g. “at all relevant times”)][GA should not assume design risk and must not warrant design is FFP for construct only engagements] [The downstream design consultant subcontract must be back to back with the express terms of the Head contract]
8.3 | Design implementation | Where our business is responsible for design, and if client approval of the design is required before construction may proceed, in the absence of an approval within a prescribed time, the baseline position is our business should be entitled to:proceed at its own risk; orclaim time and cost relief from the client if an approval is delayed beyond the time periods set out in the contract. |  |  |  |  | CD | [Limitations on proceeding with construction] [GA should avoid perpetual design review loops for resubmission of design to close out comments refreshing the period / process]
8.4 | Intellectual Property Rights (IPR) | The baseline position is our business should only agree to assign to the client copyright in, or a right to use design documentation to the extent:it owns it; orit is able to acquire it from its consultants or design subcontractors.Any IPR obligations should as much as possible be negotiated to be back-to-back with downstream consultants and suppliers, and the specific wording should be tested during the tender phase. |  |  |  |  | CD | [Assign / licence to use][Where IPR vest in client upon creation GA must retain licence to use][IPR must only vest if created specifically for the project]
8.5 | Document discrepancies | Our Business must maintain a right to claim for client clarifications of errors, ambiguities or inconsistencies in the documentation. |  |  |  |  | HCC | [Client or Contractor risk][Order of precedence][Regime to resolve / contractor entitlements or risk]
9.1 | Insurance | The baseline position is our business should (whether provided by our business or the client), required insurance for:Contract Works;Third Party Liability; andProfessional Indemnity.Where insurance is provided by the clientGamuda must be named;be confirmed acceptable by our business Head of Insurancebe maintained until:completion of work (including defects rectification for contract work and third party); andexpiry of limitation of liability period for professional indemnity insurance.Where the contract provides that insurance moneys are to be payable to the client:our business should be entitled to retain insurance proceeds in respect of work not paid for by the Client; andany obligation on our business to reinstate the works should be dependent on our business having the right to make claim for payment and / or receiving insurance proceeds as reinstatement occurs. |  |  |  |  | HF | [List policies (coverage, amounts, exclusions, limits, deductibles and who pays) / who provides][Do the contract insurance policies describe combined deductibles, when summed across the policies applying to the contract, that exceed 1% of the original contract value, or AU1.0m, whichever is the lesser][Is there a ‘gap risk’ between the client’s contract conditions and the proposed Principal Arranged Insurance policies that has not been retired with the client][Bid team to forward all insurance documentation and requirements to GA’s insurance broker for review and comment] [Tender team to consider whether Difference in Conditions (DIC) is available or required]
9.2 | Care of the works | The baseline position is our business may accept the risk of loss or damage to the permanent and temporary works until the earlier of:completion; handover (partial or whole); oroccupation/use by the client or the client’s Other Contractors.our business may accept the obligation to make good loss or damage to the works, except where the loss is caused by:negligent act or omission of the client (or its agents, consultants or invitees);Uninsurable Force Majeure Events,use or occupation by the client (or its other contractors, agents, consultants, or invitees); ordefects in design provided or directed by the Client. |  |  |  |  | CD | [Obligation / exceptions for reinstatement of loss or damage][Start and end of period of obligations]
9.3 | Reinstatement / Excepted Risks | Our Business must not accept risk or an obligation to reinstate for Excepted Risk Events that are not covered by insurance e.g. war, invasion, act of foreign enemies, ionising radiation or contamination by radioactivity etc. |  |  |  |  | HGP | [Insurance proceeds / obligation to reinstate][Obligations for uninsurable risks / excepted risks]
10.1 | Default and Termination | The baseline position is our business may accept the following as Events of Default:Failing to commence or to expeditiously and diligently progress our business’s work;Default in the performance of any of its other material obligations;An event of insolvency occurs, whether or not our business is then in Breach; andBreach of representation or warranty that has a material adverse effect on the ability of our business to carry out the Works.our business must not accept look forward or anticipatory Breach default provisions. Should the Client require an anticipatory breach regime, it must be reviewed by the Head of C&C (or nominee).our business must not accept cross defaults between contracts (termination of one contract for default on another contract).our business must have notice of an event of default and a reasonable cure period (except for insolvency) before the client is entitled to exercise termination rights.our business may accept termination for convenience subject to entitlement to payment for:all costs to date, including written down value of plant; andreasonable loss of profit related to the uncompleted work or remaining term.our business must have express suspension / termination rights for:default by the client in the performance of material obligations, other than where caused by our business;an event of insolvency occurs in relation to the client; orthe client failing to make payment due under the contract. |  |  |  |  | CD | [Does the contract include either an inequitable termination regime, or disproportionate list of breach events triggers for our business termination (either default or convenience)][Does the contract describe a timeframe for our business to remedy following notification by the client of a our business Default Event][Does the client’s right to terminate (whether for convenience of otherwise) allow the Head Contractor to take possession of our business plant and equipment][Does the client’s right to terminate the contract for convenience require payment to our business for work completed to date but not paid for by the client][Does the client’s right to terminate the contract for convenience require payment to our business for ‘break costs’ payable to downstream vendors][Does the client’s right to terminate the contract for convenience require payment to our business for demobilisation, including that of downstream vendors]Termination for Convenience:[Outline compensation]Termination for Contractor Default:[List events][Cure rights / periods][Outline process]Termination for client Default:[Contractor’s rights, including suspension for non-payment][GA to have first right of refusal to remedy defects before triggering a right of default]
11.1 | Dispute Resolution | The baseline position is our business may accept binding dispute resolution by:negotiation (with or without mediation); ordispute review board/expert determination,subject to:agreement of the expert, or appointment by an appropriate independent party; andentitlement to dispute any determination of a claim for more than $1,000,000; and/orlitigation, subject to the stipulated jurisdiction and applicable law being Australia. |  |  |  |  | HCC | [Document escalation process][Jurisdiction]
12.1 | General Liability Cap | The baseline position is our business should must cap its aggregate liability arising out of or in connection with the contract to the client to no more than:For Projects below AUD50M – 100% of the Original Contract Sum (inclusive of the proceeds of insurance) or AUD50m, whichever is the lesser.For Projects above AUD50M - 50% of the Original Contract Sum (inclusive of the proceeds of insurance) or AUD500m, whichever is the lesser.The cap may exclude:liability for death, injury and third party property damage;Wilful Misconduct or fraud;liability for breach of environmental and OH&S legislation;breach of intellectual property requirements,and the client should remain liable for a proportion of the loss suffered to the extent that its own acts or omissions have caused or contributed to the loss.Where the liability cap carve outs exceed those above, the Head of C&C must review and the tender team must include a briefing and obtain approval from the our business Management.A client may not cap its overall liability to our business. |  |  |  |  | HGP | [Does the contract provide for an overall cap on liability][Limits of liability (dollar amount / %) / inclusions / exclusions][Survive termination]
12.2 | Consequential Loss | The baseline position is our business must exclude liability for consequential loss, i.e. loss of production, use, sales, opportunity, revenue, profit or expected profit or third party pure economic loss (except to the extent covered by liquidated damages) and losses that do not naturally arise from an event or Breach.our business may accept carve outs from this exclusion to the extent those losses arise from:a breach of contract or negligent conduct by our business.Where the consequential loss carve outs exceed those above, the Head of C&C must review and the tender team must include a briefing and obtain approval from the our business Management. |  |  |  |  | HGP | [Is our business being asked to accept liability for any form of consequential damages arising out of or in connection with the Contract from any cause including breach or negligence (whether capped or uncapped liability) e.g. loss of business opportunity, goodwill, corruption of data, or loss of actual or anticipated profit or revenue, loss of production, loss arising from business interruption, pure economic or financing costs][Definition][Cap][List carve-out exclusions][Are carve outs for consequential loss is covered by insurance]
12.3 | Indemnities | The baseline position is our business must not accept contract conditions where:the contract contains an indemnity that is consequential in nature; orthe contract indemnity is not included and contributing to the overall cap on liability.our business may only indemnify the client for:damage to property and personal injury or death related to carrying out the Work under the Contract;intellectual property claims;breach of confidentiality, safety or environmental obligations.Indemnity clauses should provide for:proportional reduction in liability;limitation to foreseeable loss;limitation to circumstances where the client has actually suffered loss;duty to mitigate loss; andno settlement of third party claims absent consent.Where the indemnities exceed those above, the Head of C&C must review and the tender team must include a briefing and obtain approval from the our business Management. |  |  |  |  | HGP | [Does the contract contain any indemnity that is consequential in nature][Does the contract contain any indemnity that is not included and contributing to the overall cap on liability][List indemnities][Obligation to mitigate / proportionate reduction of liability for contribution to loss by client] [Preferrably, GA should not provide indemnities for ‘claims’ or ‘Claims’] [Is each indemnity subject to a proportional reduction mechanism and duty to mitigate by the client]
12.4 | Release / Waiver No Claims | The baseline position is our business should not give a release as part of its final claim that prevents it from bringing counter claims or a defence to a claim brought later by the client |  |  |  |  | HCC | [No Claims and Final Claims Releases]
12.5 | Third party claims exposure | The baseline position is our business should not be responsible for acts or omissions of “Other Contractors” except to the extent the third party is directly responsible to our business under a direct contract or interface agreement on comparable commercial terms (including in respect of liquidated damages).our business must not be liable for third party claims:for damage that is the unavoidable result of construction of the works in accordance with the contract; orrelated to the client’s right to construct the work under the contract on the site.our business liability for third party claims must be proportionally reduced to the extent that the client / its employees / agents contribute to the loss, damage, death or injury. |  |  |  |  | CD | [Does the contract provide for cost and time relief (including the cost of delay) for acts or omissions of 3rd parties not contracted to and under the control of our business, where such parties may prevent or limit our business’s access to the Site]
12.6 | Unilateral determinations by client parties | The baseline position is our business should not accept contract conditions that give express right(s) to client parties to make binding, or unreasonable unilateral determinations, or limit our business’s right to challenge such determinations through the use of an equitable and timely dispute resolution process. |  |  |  |  | CD | [Does the contract give express right to client parties to make binding and/or unilateral determinations and/or limit our business’s right to challenge such determinations through the use of an equitable and timely dispute resolution process]
12.7 | Material Adverse Effect/Change | The baseline position is our business should not accept contract conditions that limit or prevent our business’s entitlement to cost and/or time relief in the event of a MAC Event. |  |  |  |  | CD | [Does the contract contain clauses that limit or prevent our business’s entitlement to cost and/or time relief in the event of a MAC event]